## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | DATA ANALYSIS
INTERN NAME: | VARUN PAI
PROJECT NAME:
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2025-08-25
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | ANALYSIS OF INTERN DATA |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER
PROJECT SPONSOR
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2025-08-10 | Dataset cleaning | Data Quality | NO | Standardize data collection formats (income, graduation year, event names) | Create a pre-cleaning checklist | Intern | Solved | Missing values delayed analysis
2 | 2025-08-15 | Handling missing values | Data Processing | YES | Use consistent methods (mean/median imputation, coercion) | Document missing value handling strategy | Intern | Solved | Some income entries still ambiguous
3 | 2025-08-20 | Event participation analysis | Methodology | NO | Align event categories clearly to avoid overlap | Reclassify and group events properly | Intern + Supervisor | Pending | Needs validation with organizers
4 | 2025-08-25 | Salary expectation analysis | Interpretation | YES | Communicate assumptions (e.g., mapping family income ranges to midpoints) | Add notes in report methodology section | Intern | Solved | Important for stakeholder clarity
5 | 2025-08-28 | Visualization outputs | Presentation | NO | Use clear legends, labels, and consistent colors | Review and finalize charts before reporting | Intern | Solved | Feedback from supervisor applied