## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 3 | 0 | 1 | 1 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | ANALYSIS OF INTERN DATA |  | Project Id: | IP6707 | Project Manager: | Harshada Topale |  |  | Assumption | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 0 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 3 |  | Last Updated date: | 2025-08-19 | Project Team Lead: |  |  |  | Dependency | 0 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 3 |  |  |  |  | 2
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Inability to do required maiIncomplete, inconsistent, or poor-quality data in the source Excel file (DAD.xlsx). This could include missing Email IDs, invalid CGPA values, non-numeric entries in Experience with python, or misclassified categories in Family Income and Events.ntenance on time. | Impact on the project schedule, cost, and validity of insights. The entire analysis (Q1-Q18) depends on clean data. Poor data would require significant time to clean, delay all conclusions, and potentially lead to incorrect recommendations, undermining the project's value. | 1. Data Validation Script: Develop a script to run initial checks on the Excel file (e.g., check for duplicates, nulls, valid ranges for CGPA). 2. Data Profiling: Use df.describe() and df.info() immediately upon loading to understand data completeness. 3. Clear Assumptions: Document any assumptions made during data cleaning (e.g., mapping '7 Lakh+' to a numerical value) | Data Analyst / Project Manager | High | 16 | Open | Risk
2 | Risk | Long supply delivery time for critical information. In this context, "supply" refers to the timely provision of the correct and final dataset from the event organizers or clients. | Impact on project schedule. The project cannot start without the data. Any delays in receiving the dataset directly delay the entire analysis phase and the delivery of results. | 1. Define Requirements Early: Clearly communicate the required data format and fields needed before the project start date. 2. Establish a Single Point of Contact: Identify a key person from the client's side responsible for providing the data.3. Plan for Contingency: Buffer the project timeline to account for potential delays in data acquisition. | Project Manager | Moderate | 12 | Closed | Assumption
3 | Risk | Inability to do required maintenance on time. This refers to the maintenance of the codebase and analysis scripts (e.g., iac_(q10_q18).py, IAC(Q1-Q9).py). | Impact on the project schedule and cost. If code becomes disorganized, has bugs, or isn't documented, future updates or validating results becomes time-consuming and error-prone. | Have a dedicated maintenance plan for the code. This includes: 1. Version Control: Using Git to track changes. 2. Code Comments: Clearly commenting code, as seen in your scripts. 3. Modular Design: Creating functions for repeated tasks. The project budget should include time for code documentation and refinement. | Data Analyst | Moderate | 9 | Open | Issue
4 | [8 empty] | Dependency
5
6 | [8 empty] | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24